## Slide 1
SAP Regional Innovation Group
RIG Engagement Portfolio
Executive Review
SAP BTP Product Management | APJ & Global
July 2026
RIG Project Tooling | Confidential

## Slide 2
Portfolio Snapshot
All engagements: Joule Agent and Skill on SAP S/4HANA via SAP BTP
14
Total Engagements
+2 this quarter
9
Active
+1 this month
2
Completed
+3 YTD
2
Blocked
Needs Attention
2
Customers Live
Go Live
RIG Project Tooling | Confidential

## Slide 3
Engagement Status Overview
Chart: 
| In Progress | Completed | Blocked | Not Started
Status | 9 | 2 | 2 | 2
14
Total
Status Summary
Status
Count
% of Portfolio
In Progress
9
64%
Completed
2
14%
Blocked
2
14%
Not Started
2
14%
RIG Project Tooling | Confidential

## Slide 4
Full Engagement Portfolio — 14 Active Engagements
#
Customer
Project / Agent
Owner
Industry
Reg
Status
Prog.
1
Tata Steel
Material Management & Sales Operations Agent
Rahul Mehta
Manufacturing
APJ
In Progress
70%
2
Wipro
Sales Quotation Expiry Assistant
Sarah Chen
Retail
APJ
Completed
100%
3
Accenture
SAP Search Agent
Amir Khan
Professional Services
Global
Completed
100%
4
Mahindra & Mahindra
Open Sales Order Read & Delivery Block Agent
Priya Sharma
Retail
APJ
In Progress
55%
5
DBS Bank
Collection Mgmt Dispute Case Creation Agent
David Park
Banking
APJ
In Progress
45%
6
Standard Chartered
Customer Overdue Receivable Insights Agent
Rahul Mehta
Banking
APJ
In Progress
80%
7
Siemens
Mass Purchase Order Closure Agent
Sarah Chen
Manufacturing
Global
In Progress
60%
8
OCBC Bank
Noted Item Creation Agent
Amir Khan
Banking
APJ
Blocked
35%
9
Deloitte
Security Assistant Agent
Priya Sharma
Professional Services
Global
In Progress
65%
10
Reliance Industries
Update Sales Order Delivery Block Agent
David Park
Retail
APJ
Blocked
40%
11
EY
Audit SAP Security Agent
Rahul Mehta
Professional Services
Global
Not Started
0%
12
HDFC Bank
Customer Collection Inbound Email Agent
Sarah Chen
Banking
APJ
In Progress
75%
13
LG Electronics
Delivery Fulfillment – Delivery Pick Agent
Amir Khan
Manufacturing
APJ
In Progress
50%
14
SP Group
SAP BPEM Agent
Priya Sharma
Utilities
APJ
Not Started
0%
RIG Project Tooling | Confidential

## Slide 5
Average Portfolio Progress by Month (2026)
Chart: 
| January | February | March | April | May | June
Avg. Completion % | 22 | 31 | 38 | 45 | 52 | 58
Overall average completion across active engagements: 61%
RIG Project Tooling | Confidential

## Slide 6
Industry Breakdown — Engagements by Sector
Chart: 
| Utilities | Professional Services | Retail | Manufacturing | Banking
Engagements | 1 | 3 | 3 | 3 | 4
Banking
4
DBS Bank, Std. Chartered,
OCBC Bank, HDFC Bank
Manufacturing
3
Tata Steel, Siemens,
LG Electronics
Retail
3
Wipro, Mahindra & Mahindra,
Reliance Industries
Prof. Services
3
Accenture, Deloitte, EY
Utilities
1
SP Group
⚠ Banking has highest risk concentration — 2 of 4 banking engagements are Blocked or at risk.
RIG Project Tooling | Confidential

## Slide 7
Engagements Requiring Immediate Attention
BLOCKED (2 Engagements)
BLOCKED
OCBC Bank
Noted Item Creation Agent
Progress: 35%
Blocker: Customer FI configuration for noted items pending sign-off from finance team.
Owner: Amir Khan | Deadline: July 30, 2026
BLOCKED
Reliance Industries
Update Sales Order Delivery Block Agent
Progress: 40%
Blocker: Dependency on Open Sales Order Read agent — awaiting UAT sign-off before integration testing.
Owner: David Park | Deadline: August 31, 2026
NEAR-DEADLINE — Behind Schedule (Amber Alert)
HDFC Bank
Customer Collection Inbound Email Agent
Progress: 75%
Deadline: July 20, 2026
18 days away
Standard Chartered
Customer Overdue Receivable Insights Agent
Progress: 80%
Deadline: July 31, 2026
29 days away
RIG Project Tooling | Confidential

## Slide 8
Consultant Capacity Overview
Chart: 
| David Park | Priya Sharma | Amir Khan | Sarah Chen | Rahul Mehta
Active Engagements | 2 | 2 | 3 | 3 | 3
Threshold: Overloaded ≥ 6 | Balanced 3–5 | Underutilized < 3
Team Summary
Consultant
Active
Status
Rahul Mehta
3
Balanced
Sarah Chen
3
Balanced
Amir Khan
3
Balanced
Priya Sharma
2
Balanced
David Park
2
Balanced
5
Total Consultants
2.6
Avg. Engagements / Person
RIG Project Tooling | Confidential

## Slide 9
Delivered to Customers — Completed Engagements
01
Wipro
Sales Quotation Expiry Assistant
Successfully deployed to production environment.
Fetches sales quotations nearing expiry from SAP S/4HANA via Joule.
Reduces manual tracking effort and improves sales team response time.
Region: APJ
Owner: Sarah Chen
02
Accenture
SAP Search Agent
Enables real-time SAP knowledge search via Joule embedded in S/4HANA.
Reduces research time and improves team productivity significantly.
Reusable pattern; potential for broader rollout across consulting practices.
Region: Global
Owner: Amir Khan
RIG Project Tooling | Confidential

## Slide 10
Portfolio Intelligence Highlights
Powered by SAP Business AI
HIGH
RISK
2 engagements currently blocked and require immediate attention.
OCBC Bank & Reliance Industries
HIGH
TIMELINE
2 projects approaching deadline — risk of delay without intervention.
HDFC Bank & Standard Chartered
MEDIUM
PORTFOLIO
Banking customers have highest engagement volume — 4 active projects.
DBS Bank, Std. Chartered, OCBC Bank, HDFC Bank
LOW
PERFORMANCE
Average project completion rate across active engagements is 61%.
Steady month-over-month growth since January 2026
LOW
DELIVERY
2 engagements near completion (75%+) — plan knowledge transfer now.
HDFC Bank (75%), Standard Chartered (80%)
RIG Project Tooling | Confidential

## Slide 11
Recommended Actions
CRITICAL
1
Escalate 2 blocked engagements (OCBC Bank, Reliance Industries) with immediate stakeholder review.
2
Conduct risk review for HDFC Bank and Standard Chartered — deadlines within 30 days.
HIGH PRIORITY
1
Resolve OCBC Bank FI configuration blocker — schedule finance team sign-off meeting within 48 hours.
2
Complete Reliance Industries dependency (Open Sales Order Read UAT) to unblock integration testing.
3
Begin knowledge transfer and Go Live documentation for near-complete engagements.
STANDARD
1
Schedule quarterly portfolio review with regional APJ leadership.
2
Explore expansion opportunities with Wipro and Accenture (completed customers).
RIG Project Tooling | Confidential

## Slide 12
Engagements Starting Soon — Pipeline Overview
Not Started engagements scheduled for onboarding in Q3 2026:
Customer
Project / Agent
Owner
Start Date
End Date
Status
EY
Audit SAP Security Agent
Rahul Mehta
July 1, 2026
December 31, 2026
Not Started
SP Group
SAP BPEM Agent
Priya Sharma
July 15, 2026
January 15, 2027
Not Started
Note — EY: Engagement confirmed — awaiting environment access.
Note — SP Group: Pending access to customer SAP S/4HANA Utilities sandbox.
Both engagements are type: Joule Agent and Skill on SAP S/4HANA via SAP BTP | Region: APJ & Global
RIG Project Tooling | Confidential

## Slide 13
Thank You
SAP BTP Product Management – APJ Team
SAP Regional Innovation Group
Questions? Reach out to the RIG Team on SAP Internal channels.
www.sap.com/btp
RIG Project Tooling | Confidential